## Start Here
OPERATOR KIT 001 ¦ UNPLANNED WORK TRIAGE
A practical system for getting surprise work out of inboxes, chats, and people’s heads.
1. Define one front door
Choose where requests enter. Every unplanned request gets one row in Intake Log before work begins—unless immediate safety action is required.
2. Triage consistently
Confirm safety impact, service impact, deadline, effort, and owner. The score is a prompt for judgment, not an autopilot decision.
3. Make the next action explicit
Record what happens next: dispatch, estimate, clarify, schedule, decline, or escalate. A status without a next action is just decorative administration.
4. Review weekly
Use Weekly Review for aging, open high-priority work, and blocked items. Pick one recurring source of unplanned work to eliminate each week.
Scoring guide
Safety impact adds 50 points. High service impact adds 30, medium adds 15, and low adds 5. A deadline within one day adds 20; within three days adds 10. Use the score to surface risk, then apply human judgment using the Triage Rules sheet. Never let a score override safety policy, contractual requirements, or an informed manager decision.

## Intake Log
UNPLANNED WORK INTAKE LOG
Replace the sample rows, then use one row per request. Orange cells are calculated automatically.
Request ID | Received | Customer / Site | Request | Safety Impact | Service Impact | Deadline | Effort Hours | Owner | Status | Priority Score | Next Action | Notes
SAMPLE-001 | 2026-07-18 | North Plant | Cooling alarm in packaging area | No | High | 2026-07-19 | 3 | A. Rivera | Triaged |  | Confirm technician and access window | Delete sample rows before use
SAMPLE-002 | 2026-07-18 | Warehouse 2 | Add two rack labels before cycle count | No | Low | 2026-07-24 | 1 | J. Patel | New |  | Confirm exact rack locations | Delete sample rows before use
SAMPLE-003 | 2026-07-18 | South Yard | Damaged guard near vehicle lane | Yes | High | 2026-07-18 | 2 | M. Chen | Escalated |  | Secure area and follow safety procedure | Delete sample rows before use
Formulas:
Priority Score = IF([Received]="","",IF([Safety Impact]="Yes",50,0)+IF([Service Impact]="High",30,IF([Service Impact]="Medium",15,IF([Service Impact]="Low",5,0)))+IF([Deadline]<>"",IF([Deadline]-TODAY()<=1,20,IF([Deadline]-TODAY()<=3,10,0)),0))

## Triage Rules
TRIAGE RULES
Agree these rules with the people accountable for safety, customers, staffing, and schedule commitments.
Priority | Typical trigger | Target response | First action | Escalate when | Owner
P0 — Immediate | Safety risk, active outage, major service interruption | Act now | Secure people/area; invoke approved response | Always follow safety or incident policy | Duty manager
P1 — Today | Score 70+ or material customer/production risk | Triage within 30 minutes | Assign owner and explicit next action | Capacity or authority is missing | Operations lead
P2 — This week | Score 40–69; deadline within three days | Triage same business day | Schedule, estimate, or clarify | Deadline or commitment is at risk | Team lead
P3 — Planned | Score below 40; low impact and flexible date | Review in weekly planning | Bundle, schedule, defer, or decline | Request ages beyond agreed limit | Planner

## Weekly Review
WEEKLY UNPLANNED WORK REVIEW
Use this sheet in a 20-minute weekly review. Metrics read from Intake Log.
| METRIC | CURRENT | WEEKLY QUESTIONS
| Open requests |  | Which open request creates the most risk if it waits?
| Open score 70+ |  | What is blocked, and who can unblock it?
| Blocked |  | Which request entered through the wrong channel?
| Completed |  | What recurring cause should we eliminate instead of processing again?
| Unassigned open |  | What will we decline, defer, or renegotiate this week?
ONE IMPROVEMENT TO TEST NEXT WEEK
Write one small change to the intake, triage, scheduling, or handoff process. Name an owner and the evidence that will show whether it helped.